## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: |  | 56 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE |  | PERIODS
[7 empty] | 2018 |  |  | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022
[7 empty] | october | november | december | january | february | march | april | may | june | july | august | september | october | november | december | january | february | march | april | may | june | july | august | september | october | november | december | january | february | march | april | may | june | july | august | september | october | november | december | january | february | march | april | may | june | july | august | september | october
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Activity 01 | 0 | 0 | 1 | 5 | 100% | Prep. Cources
Activity 02 | 0 | 0 | 5 | 5 | 100% | Literature review
Activity 03 | 0 | 0 | 9 | 4 | 50% | Idea development
Activity 04 | 0 | 0 | 12 | 4 | 0% | Ident. Of Industry Standards
Activity 05 | 0 | 0 | 16 | 6 | 0% | Interviews industry expert
Activity 06 | 0 | 0 | 21 | 7 | 0% | Framework design
Activity 07 | 0 | 0 | 28 | 15 | 0% | Devising framework's Rule-sets
Activity 08 | 0 | 0 | 42 | 8 | 0% | Finalizing the Rule-sets
Activity 09 | 0 | 0 | 0 | 0 | 0% | choice of platform and testing
Activity 10 | 0 | 0 | 0 | 0 | 0% | software implementation
Activity 11 | 0 | 0 | 0 | 0 | 0% | Case Study
Activity 12 | 0 | 0 | 0 | 0 | 0% | Discussion and evaluation
Activity 13 | 0 | 0 | 0 | 0 | 0% | Thesis writing
Activity 14 | 0 | 0 | 0 | 0 | 0%
Activity 15 | 0 | 0 | 0 | 0 | 0%
Activity 16 | 0 | 0 | 0 | 0 | 0%
Activity 17 | 0 | 0 | 0 | 0 | 0%
Activity 18 | 0 | 0 | 0 | 0 | 0%
Activity 19 | 0 | 0 | 0 | 0 | 0%
Activity 20 | 0 | 0 | 0 | 0 | 0%
Activity 21 | 0 | 0 | 0 | 0 | 44%
Activity 22 | 0 | 0 | 0 | 0 | 0%
Activity 23 | 0 | 0 | 0 | 0 | 12%
Activity 24 | 0 | 0 | 0 | 0 | 5%
Activity 25 | 0 | 0 | 0 | 0 | 0%
Activity 26 | 0 | 0 | 0 | 0 | 50%